## Data Structure Summary
Risk Database | Program Assessment
Date | Period
Year | Year
Project/Program | Project/Program
Project Description | Project Description
NASA Mission Directorate(s) | NASA Mission Directorate(s)
Organization | Organization
Project Phase | Project Phase
Risk ID | Technology
Risk Name/Title | Technology Readiness Level
Risk Description/Statement | Performance Area
Context | Severity
Status | Rationale
Status Date | Classification
Status Description
Mitigation Steps
Open Date
Planned Closure Date
Likelihood
Consequence
Severity
Criticality
Affinity
Approach
Trend
Classification
Data fields indicating time of when the risk/assessment occurs
Metadata around program attributes to aide in risk classification
Data to be extracted and populated in template
Risk classifications performed (e.g., language models)

## Risk Database
Date | Year | Project/Program | Project Description | NASA Mission Directorate(s) | Organization | Project Phase | Risk ID | Risk Name/Title | Risk Description/Statement | Context | Status | Status Date | Status Description | Mitigation Steps | Open Date | Planned Closure Date | Likelihood | Consequence | Severity | Criticality | Affinity | Approach | Trend | Classification
|  |  |  | Aeronautics Research | AFRC | Approval |  |  |  |  | Active | Date |  |  | Date |  | 1 | 1 | L x C | Autopopulated | T - Technical | M - Mitigate | Decreasing (Improving) | NLP
|  |  |  | Aeronautics Research, Exploration Systems | ARC | Evaluation |  |  |  |  | Closed | [5 empty] | 2 | 2 |  | >=15 = High | C - Cost | W - Watch | Increasing (Worsening)
|  |  |  | Aeronautics Research, Exploration Systems, Space Operations | GRC | Formulation | [10 empty] | 3 | 3 |  | >5, <15 = Med | Sa - Safety | A - Accept | Unchanged
|  |  |  | Aeronautics Research, Human Exploration and Operations | GSFC | Formulation » Phase A | [10 empty] | 4 | 4 |  | <= 5 = Low | Sc - Schedule | R - Research | New Since Last Period
|  |  |  | Aeronautics Research, Human Exploration and Operations, Science | HQ | Formulation » Phase B | [10 empty] | 5 | 5
|  |  |  | Aeronautics Research, Human Exploration and Operations, Science, Space Technology | IVV | Formulation » Pre-Phase A
|  |  |  | Aeronautics Research, Human Exploration and Operations, Space Technology | JPL | Implementation
|  |  |  | Aeronautics Research, Science | JSC | Implementation » Phase B
|  |  |  | Aeronautics Research, Science, Exploration Systems | KSC | Implementation » Phase C
|  |  |  | Aeronautics Research, Science, Exploration Systems, Space Operations | LaRC | Implementation » Phase D
|  |  |  | Aeronautics Research, Science, Space Operations | MSFC | Implementation » Phase E
|  |  |  | Aeronautics Research, Space Operations | NESC | Implementation » Phase F
|  |  |  | Exploration Systems | SSC | Implementation » Pre-Phase A
|  |  |  | Exploration Systems, Space Operations | WFF | Not Applicable
|  |  |  | Human Exploration and Operations | WSTF | Not Applicable » Pre-Phase A
|  |  |  | Human Exploration and Operations, Science |  | Not Specified
Human Exploration and Operations, Science, Space Technology
Human Exploration and Operations, Space Technology
Science
Science, Exploration Systems
Science, Exploration Systems, Space Operations
Science, Space Operations
Science, Space Technology
Space Operations
Space Technology

## Project Assessment
Year | Period | Project/Program | Project Description | NASA Mission Directorate(s) | Organization | Project Phase | Technology | Technology Readiness Level | Performance Area | Severity | Rationale | Classification
[9 empty] | Cost | High (Red)
[9 empty] | Schedule | Med (Yellow)
[9 empty] | Technical | Low (Green)
Programmatic
SynBio Monthly Status Reports
Syn Bio Mid-Year Review Presentation
Astrobee FY19 Annual Review
Atrobee FY16 3rd Quarter Review

## Risk Database Source Examples
Source: 20160718_HET2_GCD FY16 Q3 Review
Source: SynBio FY21 Mid-Year Review Presentation

## Project Assess Examples
SynBio Monthly Status Reports
Syn Bio Mid-Year Review Presentation
Astrobee FY19 Annual Review
Atrobee FY16 3rd Quarter Review

## Risk Classification Ideas
Technical | Requirements
Design
Software
Test and Evaluation
Production
Performance Parameters
Interoperability
System Dependencies
System Integration
Information Assurance
Certification/ Accreditation
Expandability
Standards/Protocols
Cost | Budget
Funding
Estimating Risk/Uncertainty
Contractor
Sch | Acquisition Timeline
Fielding Timeline
Delays
Operational | Threats
Environment
Mission Effectiveness
Technical Obsolescence
Reliability
Sustainability
Availability
Safety/Health
Training
Vulnerabilities
System Redundancies
Progm/Other | Advocacy
Acquisition Process
Strategic Vision
Service Strategic Vision
Assumptions
Organizational Issues